## Slide 1
Constructive Cost Model
(COCOMO)
Problem
How to determine the effort to create software?
Identify software product to be estimated.
Estimate the Software Lines Of Code (SLOC).
Select COCOMO model: basic or intermediate
Determine product attributes. For the basic model:
  Organic – small team / good experience / flexible requirements
  Semi-detached – medium team / mixed experience & requirements
  Embedded – tight constraints
Create COCOMO estimates using the equations associated with the model
  Labor is in person-months
  Schedule is in calendar months
COCOMO
estimation
The Constructive Cost Model (COCOMO) is a SW estimation model which uses SW lines of code to estimate the needed man-power effort and duration.
Since programming paradigms evolve, COCOMO may be less useful than it was in the past.
Difficulty
Easy to use
Copyright © 2022 Dan Zwillinger. All rights reserved.
Updated: 202210
Lines of code
System attributes
Time estimate
Labor estimate
Basic COCOMO equations
Labor = a (KSLOC)b
Schedule = c (Labor)d
where
Software project type | a | b | c | d
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi-detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32
Terminology
SLOC = software lines of code
KSLOC = kilo SLOC = 1,000 lines of code
1

## Slide 2
COCOMO – Example – Creating SW program
Copyright © 2022 Dan Zwillinger. All rights reserved.
Problem statement:
You are creating a SW product; the code will be about 10,000 lines (10 KSLOC).
How long it will take to create the SW and how much manpower is required?
Answer:
If the SW product/team is organic (an experienced small team that has worked together on similar products in the past) then the parameters to use in the COCOCO equations are {a=2.4, b=1.05, c=2.5, d=0.38}. Using them
  Labor (in man-months) = a (KSLOC)b = 2.4 (10)1.05 = 27
  Schedule (in calendar months) = c (Labor)d = 2.5 (27)0.38 = 8.7
The conclusion is that a team of size 3 is needed for 9 months.
Notes
For a semi-detached SW product/team (of the same size)
  Labor = 40 man-months and Schedule = 9 calendar months
For an embedded SW product/team (of the same size)
  Labor = 57 man-months and Schedule = 9 calendar months
Conclusion: The SW development will take 9 months; the team size varies based on the type of SW being developed.
2

## Slide 3
COCOMO – Notes
Slide 1
Slide 2
COCOMO was first developed by Barry Boehm in 1981.
The basic COCOMO equations are very simple.
Basic COCOMO is good for quick, rough order of magnitude estimate of software development activities.
Basic COCOMO is estimated to be within a factor of two of the actual value, 60% of the time.
SLOC is not a great way to assess code, and it varies from language to language, but it often works well enough. “Function Points” are another way to assess “quantity” of code.
For a more detailed analysis, there is an Intermediate COCOMO model. It requires input on
  3 product parameters
  4 hardware parameters
  5 personnel Parameter
  3 project Parameters
There is also a Detailed COCOMO Model. It assumes a three level hierarchical decomposition and estimates are made at each of the 3 levels:
  Module level
  Subsystem Level
  System Level
The Detailed Model is estimated to be within 20% of the actual, 70% of the time.
Copyright © 2022 Dan Zwillinger. All rights reserved.
3