## Slide 1
Reverse Planning
(AKA backward design)
Problem
How to create a plan to reach a goal?
Difficulty
Some training required
Copyright © 2022 Dan Zwillinger. All rights reserved.
Updated: 202210
Identify the end objective
Define the Product Network
  Determine the tangible products required, starting with the last; define dependencies between them
Define the Activity Network
  Determine the activities necessary to create the products; define their dependencies
Populate the Network Data
  For each activity, define its duration, needed resources, and the definition of “Done”
Review and optimize the network
Reverse Planning is a high energy team-building approach to develop schedules based on network logic.
When should I use it? When …
  determining needed activities
  building a schedule
  creating a detailed plan to support an existing schedule
Reverse
Planning
Process
Aligned Team
Stakeholders
1
Tangible products = “something you can hold in your hand” = {emails, designs, reports, approvals, manufactured items, …}
Detailed Plan
Documents
Existing Plans
Objectives
Reverse Planning Process
2
3
4
2

## Slide 2
Reverse Planning – Example – Sending out a report
Copyright © 2022 Dan Zwillinger. All rights reserved.
2
This flow chart was created right to left, starting with the desired final result (box with red border).
First, the blue boxes were created; each of them is a “thing” (noun), something you can hold in your hand.
Second, a few of the needed yellow boxes were defined; they define “who” does “what” to create what is in the blue boxes.
Finally, the sender and receiver of each blue box (defined in the yellow box) negotiate the timeline, the inputs and outputs, and where the documents will be placed (this information is in the green boxes).
It takes much work to create a complete flowchart. However, when complete, it is clear to everyone what the process is, how long it will take, and who is responsible for what activities.

## Slide 3
Reverse Planning – Notes
Slide 1
Slide 2
“Forward planning,” what we naturally tend to do, is planning to meet a goal by laying out sequential steps, starting from “now.” This often includes unneeded and wasteful steps.
Reverse planning starts with the goal and then asks the same question over and over – going backward in the process – “What is minimal effort needed to get to this step?”
A formal 3-step process for reverse planning is as follows:
  Create a sequential sets of “products” (e.g., documents, prototypes, emails)
  For each “product,” determine “what” needs to be done (e.g., “write memo”)
  For each “what”, determine who the creator and recipient are, and get them to agree on the content and timeline (e.g., Alice creates a specific design which includes XX and YY, it is created in one week, and it is used by Bob).
The length of the exercise depends on the complexity of the goal. A large project (e.g., tens of millions of dollars) may take a month by a large team.
Creating a reverse plan is an iterative process. Each iteration will likely
  re-organize the activities
  Increase the detail in each activity
Using stickie notes and string (literally!) on a large surface (e.g., an entire wall) is sometimes needed. This allows easy re-planning as more details are filled in and the whole process is better understood.
Copyright © 2022 Dan Zwillinger. All rights reserved.
3