## Slide 1
Risk Analysis & Management
Problem
How to address project risk?
Identify the risks using assumptions, historical documents, interviews, meetings, and risk database.
Score risks. Refine high- and medium-scoring risks. Include impacts on quality, time, and cost. Use either
  Risk Prioritization Grid: severity, likelihood
  FMEA: severity, likelihood, observability
Plan responses:
  Accept the risk: can tolerate, if needed
  Avoid the risk: eliminate it from happening
  Reduce the risk: use mitigation plans
  Share the risk: offload risk to other party
Execute: Address the high-scoring risks; address the medium-scoring risks, as possible.
Monitor and control risks.
Document the learning in the risk database.
Risk Analysis & Management Process
Project
Difficulty
Easy to use
Copyright © 2022 Dan Zwillinger. All rights reserved.
Updated: 2022011
A Risk Analysis determines and prioritizes risks. A risk is something that can delay, halt, or harm your project.
Risk Management is how risks are dealt with.
There are many risk classes, each with many types of risk.
Maintaining a generic & project risk database is a best practice
1
Risk database
Risks
Risk plans
Risk Prioritization Grid

## Slide 2
Risk Analysis – Example – 6in6 project effort
Copyright © 2022 Dan Zwillinger. All rights reserved.
List of risks and their evaluation
2
Map risk numbers to a risk prioritization grid
Address all high level risks
Risk #7 strategies:
Prevention: Have experienced 6 sigma practitioner review new presentations.
Mitigation: Respond immediately to audience recognition of an error.

## Slide 3
Risk Analysis – Notes
Slide 1
Slide 2
Many techniques can identify risks, including: fault tree analysis, SWOT analysis, and PEST analysis. (See 6in6 presentations.)
Risk Analysis listens to the voices of the business, customer, and regulator. See 6in6 presentation on VOC (voice of the customer).
Performing risk analysis enables appropriate resource allocation, improves stakeholder confidence, and minimizes unexpected costs.
Sharing of best practices, such as how to identify and address risks, is key for efficient risk analysis and management.
Risk classes include
  Consequential: due to company activity
  External: outside your control
  Financial: from company decisions
  Legal: from criminal activity
  Personnel: staffing & management
  Regulatory: specific to industry
  Reputation: how company is viewed
  Supply: resource related
  Technical: technology based
  As well as those created for each specific project (see the example).
Risks should be fully described, so anyone can understand each statement.
Identifying risk types first, before identifying the specific risks, can make risk identification more complete.
Copyright © 2022 Dan Zwillinger. All rights reserved.
3